## Slide 1
MODIS C7 Reprocessing Plan
Sadashiva Devadiga
NASA GSFC

## Slide 2: Outline
C61 – Processing history
C7 and Beyond – Time line
C7 – L1, Atmosphere and Land

## Slide 3: C61 – Processing history
L1B reprocessing (3 – 6 months)
  Terra 06/2017 – 08/2017
  Aqua 12/2017 – 03/2018
Atmosphere ( 6+ months)
  Terra 07/2017 – 12/2017
  Aqua 01/2018 – 03/2018
Land (~ 24 months)
  Terra and Aqua (Tier1): 02/2020 – 12/2021
  Terra and Aqua (Tier2): 2021 – in progress
    MAIAC – to complete by May/June 2023
    C62 DSR/PAR reprocessing for the full mission period (2000 – 2023) to start in May 2023, expected to complete by Dec 2023.

## Slide 4: C61 – Processing history
Land
  May be 18 months or less
  Issues
    Re-reprocessing of products/temporal periods needed to address production related and science algorithm issues revealed while reprocessing is in progress.
    Production system shutdown for periodic maintenance and system upgrades
    Production system problems, production database performance, export backlog
    Some of these needed to be transitioned to Ubuntu OS prior to start of reprocessing

## Slide 5: C7 and Beyond
C7 target start (Best Scenario)
  L1B: early 2024
  Atmosphere: Spring or Summer 2024
  Land: Fall 2024
End of Mission processing (Phase F)
  Depends on Senior Review outcome
  Funding Scenarios for science team
  Mission decommission timeline
  C7.1 (only calibration change)/C8 (calibration + discipline science) reprocessing
  Start in early 2026

## Slide 6: C7: L1
All calibration changes and LUT are in place – many of these changes are already in C61 forward processing
Science Test in progress for atmosphere, test for land team expected to start in June.
Target start date for L1 collection reprocessing is early 2024
Schedule drivers
  How much of downstream tests required (land and atmosphere)
  Still to come
    Required – geolocation change, land water mask
    Optional – any post process that usually run with L1 (e.g. subset to Langley RC)
Impact from Orbital drift is expected to be minimal or none, calibrated products are expected to be nominal

## Slide 7: C7: Atmosphere
Algorithm change development in progress at SCF
Integration Test in progress at MODAPS for some of the PGEs.
Target start date – Summer 2024
Schedule drivers
  Need for availability of C7 L1
  Number of algorithm changes and complexity
  Deviation from the current algorithm structure and use of new libraries
  Delivery schedule
  Product interdependency
  Level of testing required at MODAPS

## Slide 8: C7: Land
In planning stage
Product specific changes not determined yet
Needs Polarization Correction based on the C7 L1B
Product specific science changes – need to weigh in effort/complexity vs change in product performance
MODIS C7 to VIIRS C3