## Slide 1: MODAPS + VIIRS Land SIPS Capability and Reprocessing Plan
Sadashiva Devadiga, Sadashiva.Devadiga-1@nasa.gov
Robert Wolfe, Robert.E.Wolfe@nasa.gov

## Slide 2: Sources of Uncertainty in SIPS Planning
Center Operation status: soon moving to stage 1
  increased access to the Center for system administrators
  Improvement in schedules for shipment and delivery of hardware.
Data delivery from SIP and data ingest at DAACs
  With two new PDR servers added during the C61 land reprocessing, SIPS now uses 3 PDR servers
  Upper limit on delivery to and ingest at LP DAAC (export backlogs could result in reduced x-rate at SIPS)
System upgrades and maintenance
  Unexpected hardware failures
  Hardware upgrades and software updates: transition to Ubuntu OS in progress
Delivery dates and changes to MODIS and VIIRS PGEs
  Increase in product volumes and computing requirement for new products are not known until start of reprocessing

## Slide 3: Product delivery protocol changes
FTP was disallowed, and replaced by SFTP: Currently using SFTP (Secure file transfer protocol based on SSH) limited to IP addresses of DAACs and SIPS outside GFSC boundary. FTP is still allowed for system transfers within GSFC.
SDTP will soon replace SFTP: MODAPS has developed SDTP (Science Data Transfer Protocol) for use across EOSDIS for data transfer. Currently MODAPS uses SDTP to transfer data from and to ASIPS, and is in early testing of export to LPDAAC, NSIDC, and GIBS (GITC). Current RBD for sftp use expires in May.

## Slide 4: MODAPS and VIIRS Processing Capability
Six processing instances used for standard processing
  Under normal processing scenario MODIS and VIIRS each use three processing instances: one each for forward processing, reprocessing and science testing.
  Processing instances are reassigned from MODIS to VIIRS or vice versa if needed (e.g C61 reprocessing used two processing instances towards the later half of 2021 to provide higher x-rate)
  Additional memory and minions are added to these streams to increase the x-rate when needed. Minions are also reconfigured with larger memory for dedicated processing (e.g. to run PGEs requiring larger memory while processing tiles at higher latitude).
Two processing instances used for NRT processing (primary and secondary)
  Secondary processing stream is identical to the primary, serving as backup to the primary and also as test system for on-boarding the new products and changes to the operational PGEs.

## Slide 5: MODAPS and VIIRS Land Processing Status
L1 and Land Forward processing includes
  MODIS C6 and C61
  VIIRS C1 and C2 L1
  NRT processing: MODIS C61, VIIRS L1 C2 and Land C1
L1 and Land Reprocessing
  C61 MODIS land reprocessing completed for most products in Jan 2022. Reprocessing of Tier 2 products (MAIAC, VCF and LC) either currently processing or about to be started. C6 processing to be discontinued by end of year 2022
  C7 MODIS L1 reprocessing expected to start end of 2022 or early 2023. C7 changes to land products currently under review at SCF
  C2 VIIRS L1 reprocessing completed, Land reprocessing expected to start in Summer 2022

## Slide 6: VIIRS C2 Test and Reprocessing Plan
SNPP C2 and J1/NOAA-20 C.1 L1 reprocessing completed and currently in forward processing
C2 Land Science Test
  Cross Calibration of SNPP and J1/NOAA-20 to produce continuity to Aqua MODIS is currently in science testing (April/May 2022)
    Process 3-months of data from 2021, 2018 and 2012
  Land Chain Test using cross calibration of SNPP and J1 L1 (Aug/Sept 2022)
    Process land product suit for 3-months of winter and summer
  Science test and C2 reprocessing run on Ubuntu system with Ubuntu version of PGEs deployed from Gitlab

## Slide 7: MODIS C7 reprocessing Timeline (Tentative)
In-guide mission timing and reprocessing scenario
  End of science collection for Terra is Nov 2023 and Aqua is Jul 2023
  Phase F will end in Nov 2025 for Terra and Jul 2025 for Aqua
  C7 could be the last reprocessing, and could start after end of science collection for both Aqua and Terra MODIS
Over-Guide mission timing and reprocessing scenario
  End of science collection for Terra March 2027 and Aqua is Aug 2026
  Likely have Phase F end for both mission by end of FY 2028
  Plan C7 reprocessing to start in later 2023 or early 2024 and an end of mission reprocessing in the last year of Phase F.

## Slide 8: Forward Processing and Collection Reprocessing Timeline
01 03 05 07 09 11 01 03 05 07 09
2022 2023
MODIS – C6 at 1x for each mission
MODIS – C61 at 1x for each mission
SNPP VIIRS NASA C1 L1B - AS 5110 at 1x and C1 Land – AS 5000
SNPP VIIRS NASA L1B C2 (AS 5200) AND j1 l1b (AS 5201)
MODIS C6/C61
MAIAC on Tier2 at 40x
SNPP VIIRS C1
VIIRS C2
VIIRS Land C2 Reprocessing (AS 5200) at 20x
VIIRS Land C2 forward processing (AS 5200)
Xcal and C2 Land ChainTest
C7 L1B Reprocessing
Under Review: 20X Reprocessing for VIIRS may require two reprocessing streams for VIIRS C2 reprocessing.

## Slide 9: Questions ?